## Guidance
GUIDANCE NOTES
This annual work plan is aggregated from individual work plans of all the key program staff at the Secretariat. It is designed to allign with the Strategic objectives, outcomes and outputs of the current Strategic plan. As such, the template will also be used useful in the long run for tracking achievements Vs planned activities in each quarter.
COLOR LEGEND
Strategic Objectives
Outcomes
Outputs
Activities
Period/Duration
Action required
1. Kindly review the Final plan 2023 and update all the activities, budgets and timeline. Some activities may require to be reworded as they are too wordy. Some may need additional info to make them more specific eg where is the activity taking place, who are targeted, and what targets (quanties, numbers etc.)
2. Kindly update the Quarter one reporting matrix. This forms the basis of our quarterly narrative report
3. Please feel free to ask any questions and make suggestions on how we can improve the tools are currently structured

## Draft Annual plan 2023
Network of African National Human Rights Institutions (NANHRI) | [18 empty] | Legend | Arudi
2023 Work Plan & Budget | [19 empty] | Athewa
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  |  | Deborah
Strategic Objectives | Outcomes | Outputs | Activities (What, Who, Where and targets) | Budget | [12 empty] | Responsible | Comments |  | Gilbert
| SO1: ENHANCED CAPACITY OF NHRIs IN AFRICA TO DELIVER ON THEIR MANDATE | [18 empty] | Mercy
SO1: ENHANCED CAPACITY OF NHRIs IN AFRICA TO DELIVER ON THEIR MANDATE | 1.1 All African Countries have NHRIs that are compliant to the Paris Principles (Establishment and accreditation) | 1.1.1 Establishment of NHRIs in countries not having the NHRIs | Support the establishement process in Lesotho, Senegal and Botswana (Legal Analyses, consultative forums) | 5000 | [12 empty] | Gilbert |  |  | Loyce | bar: Feb to May; Jul; Oct
|  | 1.1.2 New NHRIs that become compliant to the Paris Principles (A Status) | [17 empty] | Grace
|  | 1.1.3 NHRIs retain their A Status | Support to NHRIs due for accreditation review: providing written submission following the statements of compliance and other documentation and attend the sessions for the NHRIs that will be reviewed; Assist in compilation of documents, drafting of the statements of compliance, simulation interview and written submission | 15000 | Jan: Morocco, Tanzania, Zimbabwe; Aug: DRC, Egypt, Malawi , Nigeria and Uganda | Gilbert
| 1.2 Increased capacity of NHRIs to deliver on their mandates | 1.2.1 Enhanced NHRIs capacity in financial Sustainability
1.2.2 Enhanced capacity of NHRIs in developing and implementing Strategic Plans
|  | 1.2.3 Enhanced NHRIs capacity to engage with governments | Visit to Comoros or Djibouti | 3000 | Sep: Comoros | Gilbert
1.2.4 Enhanced leadership capacity of African NHRIs
|  | 1.2.5 Improved NHRIs institutional arrangements | Follow up on the recommendations of the review of Liberia INCHR | 0 | [12 empty] | Gilbert
| 1.3 Increased capacity of NHRIs in addressing emerging issues | 1.3.1 Enhanced NHRI capacity to develop frameworks for dealing with emerging issues
|  |  | Co-convene the Biennial Conference 2023 with CHRAJ | [13 empty] | Loyce/David/Gilbert | bar: Oct to Nov
|  |  | In- Country Training for Togo | 16105.2008 | [12 empty] | Arudi | bar: Jan
|  |  | Support NHRIs/ NANHRI participate in the Pan African International Lesbian and Gay Association Annual Conference. | 0 | [12 empty] | Arudi | bar: Jun to Jul
|  |  | Learning and Exchange visit to Uganda to see the needed support in the protection of SOGIE after closure of SMUG | 6758 | [12 empty] | Arudi
Proposal writing, review and submission | bar: Feb to Mar
|  |  | 2 Regional Convening - Thematic trainings for the NHRIs – Regional Convenings with all the 9 NHRIs | 124484.6468 | [12 empty] | Arudi | bar: Feb to Mar
|  |  | End of project evaluation | 71850 | [12 empty] | Arudi | bar: Feb to Mar
| 1.4 Improved capacity of NHRIs to develop partnerships with stakeholders | 1.4.1 Improved NHRIs networking capacity | Participate in and encourage NHRIs to participate in the GANHRI General Meeting | 0 | [12 empty] | Gilbert | bar: Mar
|  | 1.4.2 Enhanced capacity of NHRIs to collaborate with stakeholders | Visit to Addis -meeting in Addis to meet with the DPA/PS and Attending the AU February Summit | 3000 | [12 empty] | Gilbert & David | bar: Feb; Jul
STRATEGIC OBJECTIVE 2: ENHANCE THE PROMOTION, PROTECTION AND FULFILMENT OF HUMAN RIGHTS IN AFRICA
STRATEGIC OBJECTIVE 2: ENHANCE THE PROMOTION, PROTECTION AND FULFILMENT OF HUMAN RIGHTS IN AFRICA | 2.1 Enhanced capacity of NHRIs to contribute to the realization of ECOSOC rights in African countries | 2.1.1 Enhanced capacity of NHRIs to advocate for ECOSOC rights | Hold Regional Sensitization Forum targeting NHRIs and CSOs on trade, social and environmental impacts of the AfCFTA | 28727 | [12 empty] | Deborah | bar: Mar
|  |  | Launch and dissemination of AfCFTA baseline and guiding framework | 0 | [12 empty] | Deborah | bar: Mar
|  |  | Bilateral Exchanges on National Assessments on the Impact of Covid-19 on the Rights and Welfare of Children for Ghana, Kenya, Ethiopia, Malawi & Burundi | 0 | [12 empty] | Deborah | bar: Feb
|  |  | Support the development of 5 National Stakeholders engagement stratgies/plans and creation of platforms | 38016 | [12 empty] | Deborah | bar: Feb to Apr
|  |  | Support to select NHRIs to increase their gender mainstreaming capacity vis-à-vis BHR and the blue economy | 12669.44 | [12 empty] | Mercy | bar: Jan to Feb
|  |  | High Level Political Forum on SDGs (NHRI participation in the main forum and side event) | TBC | [12 empty] | Mercy | bar: Jul to Aug
|  |  | In-country Workshop (NHRIs, COAs, Rightsholders, dutybearers to to work together to to protect SRHR | 37742 | Apr: Niger | Athewa
|  |  | In-country Workshop (NHRIs, COAs, Rightsholders, dutybearers to to work together to to protect SRHR | 37742 | May: Nigeria | Athewa
|  |  | In-country training workshop to build NHRI's capacity around legal frameworks within the African continent (Maputo Plan of Action, the role of NHRIs in drafting alternative reports and following up with UPR recommendations regarding SRHR and the gaps and entry points for NHRIs engagements based on the research findings. | 19866.2825 | Feb: Kenya | Athewa
|  |  | In-country training workshop to build NHRI's capacity around legal frameworks within the African continent (Maputo Plan of Action, the role of NHRIs in drafting alternative reports and following up with UPR recommendations regarding SRHR and the gaps and entry points for NHRIs engagements based on the research findings. | 19866.2825 | Mar: Zambia | Athewa
|  |  | In-country training workshop to build NHRI's capacity around legal frameworks within the African continent (Maputo Plan of Action, the role of NHRIs in drafting alternative reports and following up with UPR recommendations regarding SRHR and the gaps and entry points for NHRIs engagements based on the research findings. | 19866.2825 | Apr: DRC | Athewa
| 2.2 Enhanced performance of NHRIs in contributing to improvement in the democracy and rule of law in African countries | 2.2.1 Enhanced capacity of NHRIs to advocate/lobby their countries for ratification of regional and international treaties relating to human rights, democracy and rule of law | Advocacy Mission to the EAC & the African Court | 20000 | [12 empty] | Deborah | bar: Feb
|  |  | Regional convening on experience sharing on ASRH Maputo Protocol, SDGs, BPFA and Specific AU Campaigns (NHRIs, young women, dutybearers, in 4 countries on the protection of ASRHR-(SHARP) | 49824.1282 | Jul: Kenya | Athewa
|  | 2.2.2 Enhanced capacity of NHRIs to actively monitor implementation of ratified international and regional treaties relating to human rights,democracy and rule of law | Evaluation survey to harvest outcomes on RAP Activities implemented in 2019-2022 | 0 | [12 empty] | Deborah | bar: Apr to Jun
|  |  | Report on RAP Activities Implemented in 2019-2022 | 0 | [12 empty] | Deborah | bar: Jul to Sep
|  |  | Statement to the Human Rights Council Sessions | 0 | [12 empty] | Gilbert & Loyce | bar: Mar; Sep
|  |  | Statements to ACHPR- the two ordinary sessions | 0 | [12 empty] | Gilbert & Loyce
|  |  | Support NHRIs, COAs, Rightsholders, dutybearers on ratification, domestication, implementation of laws/standards (Maputo Protocol, SDGs, BPFA and Specific AU Campaigns, in 4 countries on the protection of SRHR-(HIVOS) | 50410 | Aug: Tanzania | Athewa
2.2.3 NHRIs capacity to lobby and advocate for the development of national laws and policies that are aligned to international and regional standards
| 2.3 NHRIs enhanced cooperation and usage of regional human rights mechanisms | 2.3.1 Enhanced capacity of NHRIs to identify and report cases and issues before regional human rights mechanisms, and other referrals | Conduct 1 in-person monitoring and follow-up workshop on action plans for the litigation trainings conducted for the NHRIs of Kenya, Cameroon, DRC, Ethiopia, and Ghana in the context of implementation of regional human rights commitments | 50000 | [12 empty] | Deborah | bar: May
|  |  | Support at least 3 NHRIs to submit applications for affiliate Status to the ACHPR and at least 3 NHRIs with affiliate status to submit activity/alternative reports | 0 | [12 empty] | Deborah
|  |  | Support at least 5 NHRIs to submit applications for affiliate status to the ACERWC and at least 2 NHRIs with affiliate status to prepare their inaugural activity reports to the ACERWC | 0 | [12 empty] | Deborah
|  |  | Convene 2 NHRIs (exchange) Forums at the margins of the ACHPR session, on the situation of human rights in Africa, with the outcome of recommending adoption of at least 2 resolutions by the ACHPR. One Forum will be on a Maputo Protocol theme in collaboration with the ACHPR mandate of the Special Rapporteur on the Rights of Women in Africa | 200000 | [12 empty] | Deborah | bar: Apr; Oct
|  |  | Mobilize the participation of NHRIs at the ordinary sessions of the ACHPR | 0 | [12 empty] | Deborah | bar: Mar to Apr; Oct to Nov
|  |  | Mobilize the participation of NHRIs at the ordinary sessions of the ACERWC | 0 | [12 empty] | Deborah | bar: Mar to Apr; Oct to Nov
|  |  | Convene the annual policy dialogue forum | 100000 | [12 empty] | Deborah | bar: Sep
|  |  | Publish and disseminate the findings on the use of lethal force by police in Kenya | 10000 | [12 empty] | Deborah | bar: Feb to May
|  |  | Sub- Regional Training on access to remedy: NHRI Reporting and Strategic Litigation on BHR | 21530.27 | [12 empty] | Mercy | bar: Jun to Jul
|  | 2.4.1 Enhanced capacity of NHRIs to monitor realization of human rights targets in the Sustainable Development Agenda and the African Agenda 2063 | Train 5 NHRIs on how to engage parliament on SDGs as per the provisions of the Belgrade Principles | TBC | [12 empty] | Deborah | bar: Jul
|  |  | Hold an NHRI dialogue forum with the Pan-African parliament on collaborative role in monitoring the implementation of the SDGs and Agenda 2063 | TBC | [12 empty] | Deborah | bar: Jun
|  |  | 2 In-country Exchange Workshops for strengthening the engagement of NHRIs with national statistical offices for purposes of streamlining Human rights data in voluntary national review SDG processes in Malawi & Sierra Leone | 54000 | [12 empty] | Deborah | bar: May; Sep
|  |  | Develop a 15-25 page guidance note for NANHRI members on how to monitor implementation of the blue economy/ SDG14 | 3535 | [12 empty] | Mercy | bar: Apr to May
|  |  | In-person workshop to adopt and launch guidance note on NHRI involvement in Blue Economy | 20016.28 | [12 empty] | Mercy | bar: Aug
|  |  | Ad hoc engagement and support to NANHRI members on BHR, SDGs, and the blue economy | TBC | [12 empty] | Mercy
|  |  | Support NHRIs on regional engagement on SRH (EAC SRH Bill, Maputo Plan of Action, etc) | TBC | [12 empty] | Athewa
|  | 2.4.2 NHRIs have enhanced capacity to influence African countries on realization of human rights targets and aspirations on the Agenda 2030 and 2063 | Promote African NHRIs’ delegates (commissioners and staff) participation in the annual sessions of the Africa Regional Forum on Sustainable Development (ARFSD) - 1 side event per year in 2023 & 2024 | 27000 | [12 empty] | Deborah | bar: Feb to Mar
|  |  | Support select NHRIs to participate and engage during the ordinary session of the African Commission | 27000 | [12 empty] | Deborah | bar: Oct to Nov
|  |  | NANHRI advocacy to select regional mechanisms on NHRI engagement on BHR and the SDGs (ARFSD 9, Zambia national NAP Dialogue, Central Africa NAP Dialogue, Africa BHR Forum, East and Horn NAP Dialogue, among others) | 13965 | [12 empty] | Mercy
|  |  | ARFSD 9 | [13 empty] | Mercy | bar: Feb
|  |  | Zambia NHRI National NAP dialogue | [13 empty] | Mercy | bar: Feb
|  |  | Central Africa NAP dialogue | [13 empty] | Mercy | bar: Dec
|  |  | Africa BHR Forum 2 | [13 empty] | Mercy | bar: Oct
|  |  | Conduct side event for NHRIs & COAs in conjunction with the Special Rapporteur on the Rights Women in Africa on the Margins of the 73rd Ordinary Session of the ACHPR on the theme of removal of reservations on Article 14 of the Maputo Plan of Action | 121640 | [12 empty] | Athewa | bar: Oct to Nov
STRATEGIC OBJECTIVE 3: ENHANCE THE ORGANIZATIONAL DEVELOPMENT AND INSTITUTIONAL SUSTAINABILITY OF NANHRI
STRATEGIC OBJECTIVE 3: ENHANCE THE ORGANIZATIONAL DEVELOPMENT AND INSTITUTIONAL SUSTAINABILITY OF NANHRI | 3.1 NANHRI is a knowledge power house on HR issues in Africa | 3.1.1 Knowledge management framework for NANHRI is developed | Conduct a mid-term evaluation of the NANHRI strategic plan | 18362 | [12 empty] | David
|  |  | Quarterly newsletters, including mailchimp electronic newsletter | 0 | [12 empty] | Loyce | bar: Mar; Jun; Sep; Dec
|  |  | Review of Current Communications Strategy | 0 | [12 empty] | Loyce
|  |  | Website and social media updates | 0 | [12 empty] | Loyce | bar: Jan; Apr; Jul; Oct
|  |  | Media monitoring & News updates | 0 | [12 empty] | Loyce
|  |  | Mapping of human rights Journalists in regional and international media | 0 | [12 empty] | Loyce | bar: Jan to Mar
|  |  | Develop and design Annual Report 2022 | 0 | [12 empty] | Loyce | bar: Jan to Feb
| 3.2 Enhanced programmatic Monitoring Evaluation Accountability and Learning (MEAL) | 3.2.1 MEAL framework developed
| 3.3 NANHRI Improves on financial sustainability | 3.3.1 Diversified streams of revenue for NANHRI
|  | 3.3.2 Annual and project audits to improve operational efficiency & compliance | DIHR Project Audit | 1872 | [12 empty] | Grace | bar: Jan to Feb
|  |  | RWI Project Audit | 1205 | [12 empty] | Grace | bar: Jan to Feb
|  |  | Annual Institution Audit | 2325.2033 | [12 empty] | Grace | bar: Jan to Feb
|  | 3.3.3 Personnel costs for the Secretariat staff | Personnel Costs | 346810.83 | [12 empty] | Gilbert
| 3.4 Improved service delivery by NANHRI | 3.4.1 Right sized organization structure
3.4.2 Human Resources policies and procedures developed
3.4.3 Productivity for staff enhanced
|  |  | Total Budget (USD) | 1599188.8466